## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Kory | Connor | Jimin | Matt | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
[5 empty] | (Hours) | (Hours) | (Hours) | (Hours)
Preliminary & Parallel Tasks | Architecture |  |  |  |  | 8
|  | Design architecture | Project Manager, Requirements Engineer | Kory, Connor | 8
| Requirements |  |  |  |  | 9
|  | Gather | Project Manager, Requirements Engineer | Kory, Connor | 3
|  | Analyze | Project Manager, Requirements Engineer | Kory, Connor | 3
|  | Specify | Project Manager, Requirements Engineer | Kory, Connor | 3
| Documentation |  |  |  |  | 2
|  | Project Charter | Project Manager, Team | Kory, Connor, Matt, Jimin | 3
|  | Requirements Document | Project Managers | Kory, Connor | 5
|  | Project Plan | Project Manager, Developers | Kory, Connor, Matt, Jimin | 5
|  | Architecture Document | Architect | Connor | 4
|  | Test Report | Tester | Matt, Jimin | 8
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Kory, Connor | 2
Iteration 1: | Design |  |  |  |  | 6
|  | Design Login Page (Mockup) | Project Manager, Architect | Kory, Connor | 1
|  | Design Home page/Notification dashboard (Mockup) | Project Manager, Architect | Kory, Connor | 3
|  | Design Transaction Summary Page (Mockup) | Project Manager, Architect | Kory, Connor | 2
| Development |  |  |  |  | 45 | [6 empty] | 0
|  | Determine technology needs | Team | Kory, Connor, Jimin, Matt | 1 |  | 1
|  | Research and learn new language and environment | Team | Kory, Connor, Jimin, Matt | 7
|  | Environment Setup | Team | Kory, Connor, Jimin, Matt | 2
|  | Set up springboot application | Developer | Connor | 5
|  | Write basic javascript code to test end to end application | Developers | Kory, Matt | 5
|  | Create initial login page with Angular Material | Developer | Matt | 5
|  | Create Initial Dashboard with Angular Material | Developer | Kory | 10
|  | Setup SQL Server and connect to Springboot application | Developers | Connor, Jimin | 10
| Analysis |  |  |  |  | 7
|  | Evaluate Designs with team | Team | Kory, Connor, Jimin, Matt | 1
|  | Manual Testing | Testers | Jimin, Matt | 2
|  | Bug fix as required | Testers | Jimin, Matt | 2
|  | Evaluate needs for next iteration | Project Manager | Kory | 2
Iteration 2: | Design
Development
Analysis
Iteration 3: | Design
Development
Analysis
Iteration 4: | Design
Development
Analysis
Iteration 5: | Design | [11 empty] | 0
Development
Analysis
Total | [5 empty] | 77