## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Kory | Connor | Jimin | Matt | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
[5 empty] | (Hours) | (Hours) | (Hours) | (Hours)
Preliminary & Parallel Tasks | Architecture |  |  |  |  | 8 |  | 6 |  |  |  |  | 6
|  | Design architecture | Project Manager, Requirements Engineer | Kory, Connor | 8 |  | 6 |  | 3 | 3 | - | - | 6
| Requirements |  |  |  |  | 9 |  | 9 |  |  |  |  | 9
|  | Gather | Project Manager, Requirements Engineer | Kory, Connor | 3 |  | 3 |  | 1.5 | 1.5 | - | - | 3
|  | Analyze | Project Manager, Requirements Engineer | Kory, Connor | 3 |  | 3 |  | 1.5 | 1.5 | - | - | 3
|  | Specify | Project Manager, Requirements Engineer | Kory, Connor | 3 |  | 3 |  | 1.5 | 1.5 | - | - | 3
| Documentation |  |  |  |  | 44 |  | 38 |  |  |  |  | 38
|  | Project Charter | Team | Kory, Connor, Matt, Jimin | 8 |  | 8 |  | 2 | 2 | 2 | 2 | 8
|  | Requirements Document | Team | Kory, Connor, Matt, Jimin | 10 |  | 10 |  | 2.5 | 2.5 | 2.5 | 2.5 | 10
|  | Project Plan | Team | Kory, Connor, Matt, Jimin | 8 |  | 12 |  | 3 | 3 | 3 | 3 | 12
|  | Architecture Document | Team | Kory, Connor, Matt, Jimin | 5 |  | 8 |  | 2 | 2 | 2 | 2 | 8
|  | Test Report | Team | Kory, Connor, Matt, Jimin | 8 |  |  |  | - | - | - | - | -
|  | User Guide & System Admin Doc | Team | Kory, Connor, Matt, Jimin | 5 |  |  |  | - | - | - | - | -
Iteration 1: | Design |  |  |  |  | 6 |  | 3
|  | Design Login Page (Mockup) | Project Manager, Architect | Kory, Matt | 1 |  | 1 |  | 0.5 | 0.5 | - | - | 1
|  | Design Home page/Notification dashboard (Mockup) | Project Manager, Architect | Kory, Matt | 3 |  | 1 |  | 0.5 | 0.5 | - | - | 1
|  | Design Transaction Summary Page (Mockup) | Project Manager, Architect | Kory, Matt | 2 |  | 1 |  | 0.5 | 0.5 | - | - | 1
| Development |  |  |  |  | 53 |  | 37 |  |  |  |  | 37
|  | Determine technology needs | Team | Kory, Connor, Jimin, Matt | 1 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  | Research and learn new language and environment | Team | Kory, Connor, Jimin, Matt | 15 |  | 16 |  | 4 | 4 | 4 | 4 | 16
|  | Environment Setup | Team | Kory, Connor, Jimin, Matt | 5 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Set up springboot application | Developer | Connor | 5 |  | 4 |  | - | 4 | - | - | 4
| (Carry to next Iteration) | Write basic javascript code to test end to end application | Developers | Kory, Matt | 5 |  | 0 |  | - | - | - | - | 0
|  | Create initial login page with Bootstrap | Developer | Matt | 5 |  | 3 |  | - | - | - | 3 | 3
|  | Create Initial Transactions page with Bootstrap | Developer | Kory | 5 |  | 3 |  | 3 | - | - | - | 3
|  | Setup SQL Server, implement architecture, create DDL | Developers | Connor, Jimin | 5 |  | 6 |  | - | 3 | 3 | - | 6
| (Carry to next Iteration) | Connect Spring application to database | Developers | Jimin, Connor | 5 |  | 0 |  | - | - | - | - | 0
| Analysis |  |  |  |  | 11 |  | 6 |  |  |  |  | 37
|  | Evaluate Designs with team | Team | Kory, Connor, Jimin, Matt | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Manual Testing | Testers | Jimin, Matt | 2 |  | N/A |  | - | - | - | - | -
|  | Bug fix as required | Testers | Jimin, Matt | 2 |  | N/A |  | - | - | - | - | -
|  | Evaluate needs for next iteration | Project Manager | Kory, Connor, Matt, Jimin | 5 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Iteration 2: | Design |  |  |  |  | 9 |  | 4 |  |  |  |  | 4
|  | Design Add/Edit/Remove Notification popup (mockup) | Project Manager, Architect | Kory, Matt | 2 |  | 1 |  | 0.5 | - | - | 0.5 | 1
|  | Design table row expansion (mockup) | Project Manager, Architect | Kory, Matt | 2 |  | 1 |  | 0.5 | - | - | 0.5 | 1
|  | Refine previous mockups (make more official designs) | Project Manager, Architect | Kory, Matt | 5 |  | 2 |  | 1 | - | - | 1 | 2
| Development |  |  |  |  | 59 |  | 18 |  |  |  |  | 18
| (Carry to next Iteration) | Implement Initial Notification popups | Developer | Matt | 5 |  | - |  | - | - | - | - | -
|  | Implement initial Dashboard page | Developer | Matt, Kory | 5 |  | 10 |  | 5 | - | - | 5 | 10
| (Carry to next Iteration) | Send Query information (For notifications) from front end to java layer - work with team member for endpoints | Developers | Matt, Kory | 10 |  | - |  | - | - | - | - | -
| (Partially carry to next Iteration) | Set up live SQL server for development | Developer | Connor | 5 |  | 1 |  | - | 1 | - | - | 1
| (Carry to next Iteration) | Learn how to set up project on server | Developer | Connor | 5 |  | - |  | - | - | - | - | -
| (Partially carry to next Iteration) | Configure Angular Proxy settings to hit springboot server | Developer | Kory | 2 |  | 1 |  | 1 | - | - | - | 1
| (Carry to next Iteration) | Send Query information received to SQL Server - work with team member for endpoints | Developers | Connor, Jimin | 6 |  | - |  | - | - | - | - | -
|  | Research Bootstrap, implement into project | Developer | Kory | 5 |  | 6 |  | 6 | - | - | - | 6
| (Carry to next Iteration) | Write Code to load transactions table with data from SQL server | Developer | Kory | 5 |  | - |  | - | - | - | - | -
| (Carry to next Iteration) | Write JUnit tests for endpoint calls | Developers | Matt, Jimin | 5 |  | - |  | - | - | - | - | -
| (Carry to next Iteration) | Implement Basic login functionality | Developers | Matt, Connor | 6 |  | - |  | - | - | - | - | -
| Analysis |  |  |  |  | 31 |  | 27 |  |  |  |  | 27
|  | Evaluate Designs with team | Team | Kory, Connor, Matt, Jimin | 2 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  | Work on Documentation Tasks | Team | Kory, Connor, Matt, Jimin | 20 |  | 20 |  | 5 | 5 | 5 | 5 | 20
|  | Manual Testing | Team | Kory, Connor, Matt, Jimin | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Bug fix as required | Team | Kory, Connor, Matt, Jimin | 4 |  | - |  | - | - | - | - | -
|  | Evaluate needs for next iteration | Team | Kory, Connor, Matt, Jimin | 5 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Iteration 3: | Design |  |  |  |  | N/A
| Development |  |  |  |  | 50 |  | 36 |  |  |  |  | 36
|  | Implement Initial Notification (Add/Edit) popups | Developer | Matt | 6 |  | 6 |  | - | - | - | 6 | 4
|  | Implement final Notification Rule table/popup table | Developer | Kory | 5 |  | 4 |  | 4 | - | - | - | 6
| (Carry to next Iteration) | Send Query information (For notifications) from front end to java layer - work with team member for endpoints | Developers | Matt, Connor | 8 |  | - |  | - | - | - | - | -
|  | Set up live SQL server for development | Developer | Kory | 5 |  | 8 |  | 8 | - | - | - | 8
| (ongoing) | Learn how to set up project on server | Developers | Kory, Connor | 5 |  | 2 |  | 2 | - | - | - | 2
|  | Configure Angular Proxy settings to hit springboot server | Developer | Kory | 3 |  | 3 |  | 3 | - | - | - | 3
| (Carry to next Iteration) | Send Query information received to SQL Server - work with team member for endpoints | Developers | Connor, Jimin | 2 |  | - |  | - | - | - | - | -
|  | Write Code to load transactions table with data from SQL server | Developers | Connor, Kory | 3 |  | 5 |  | 3 | 2 | - | - | 5
| (ongoing) | Implement Basic login functionality | Developers | Matt, Jimin | 8 |  | 8 |  | - | - | 8 | - | 8
| (Carry to next Iteration) | Write JUnit tests for endpoint calls | Developer | Jimin | 5 |  | - |  | - | - | - | - | -
| Analysis |  |  |  |  | 30 |  | 26 |  |  |  |  | 26
|  | Work on Documentation Tasks | Team | Kory, Connor, Matt, Jimin | 20 |  | 20 |  | 5 | 5 | 5 | 5 | 20
|  | Manual Testing | Team | Kory, Connor, Matt, Jimin | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Bug fix as required | Team | Kory, Connor, Matt, Jimin | 4 |  | - |  | - | - | - | - | -
|  | Evaluate needs for next iteration | Team | Kory, Connor, Matt, Jimin | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Iteration 4: | Design |  |  |  |  | N/A
| Development |  |  |  |  | 49 |  | 47 |  |  |  |  | 47
| (Carry to next Iteration, new story) | Integrate login code to main java application | Developers | Jimin | 5 |  | 15 |  | - | - | 15 | - | 15
|  | Add balance column and data to transaction table and models | Developer | Kory | 1 |  | 1 |  | 1 | - | - | - | 1
|  | Implement Transactions table Pagination | Developer | Kory | 3 |  | 3 |  | 3 | - | - | - | 3
|  | Implement remaining data models into Java | Developer | Connor | 2 |  | 2 |  | - | 2 | - | - | 2
| (ongoing) | Touch up css and styiling in web app | Developer | Matt | 4 |  | 2 |  | - | - | - | 2 | 2
| (Carry to next Iteration, new story) | Securely store login information on database | Developer | Jimin | 5 |  | - |  | - | - | - | - | -
|  | Implement add/edit rule functionality | Developer | Kory | 8 |  | 16 |  | 16 | - | - | - | 16
| (Carry to next Iteration, new story) | Send Query information (For notifications) from front end to java layer - work with team members for endpoints | Developers | Matt, Connor, Jimin | 3 |  | - |  | - | - | - | - | -
|  | Implement backend code to pull notifications | Developers | Connor, Kory | 5 |  | 1 |  | 0.5 | 0.5 | - | - | 1
| (ongoing) | Learn how to set up project on server | Developer | Kory | 3 |  | 1 |  | 1 | - | - | - | 1
| (Carry to next Iteration, new story) | Send Query information received to SQL Server - work with team members for endpoints | Developers | Matt, Connor, Jimin | 2 |  | - |  | - | - | - | - | -
|  | Add functionality to add new transactions | Developers | Matt, Connor | 3 |  | 3 |  | - | 1.5 | - | 1.5 | 3
| (ongoing) | Write JUnit tests | Developer | Connor, Kory | 5 |  | 3 |  | 1.5 | 1.5 | - | - | 3
| Analysis |  |  |  |  | 10 |  | 10 |  |  |  |  | 10
|  | Manual Testing | Team | Kory, Connor, Matt, Jimin | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Bug fix as required | Team | Kory, Connor, Matt, Jimin | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Evaluate needs for next iteration | Team | Kory | 4 |  | 4 |  | 4 | - | - | - | 4
Iteration 5: | Design |  |  |  |  | N/A
The final haul | Development |  |  |  |  | 73
| REQUIRED | Finish by 4/26 if possible |  |  |  | 45
|  | Login Page functionality | Developers | Jimin, Kory, Connor | 15
|  | Notification Search Filters functionality | Developers | Kory, Connor | 10
|  | Implement front end functionality for displaying notifications | Developer | Matt | 5
|  | Enhance modal features to auto update tables | Developer | Matt | 2
|  | Export notification data to spreadsheet | Developer | Kory | 5
|  | Create MySQL trigger for duplicate transactions | Developer | Kory | 3
|  | JUnit Tests - 10% Coverage needed | Developers | Connor, Jimin | 5
| IF TIME PERMITS | Finish by 5/1 if possible |  |  |  | 28
|  | Touch up page styling and presentation | Team | Anyone | 5
|  | OWASP ZAP Scan and critical fixes | TBD - Who has time | TBD - Who has time | 5
|  | Make tabs for transactions page to split accounts | TBD - Who has time | TBD - Who has time | 2
|  | Implement some form of "choose account" feature for rules | TBD - Who has time | TBD - Who has time | 8
|  | Mark as read functionality | TBD - Who has time | TBD - Who has time | 3
|  | Deploy full application on linux server | Developer | Kory | 5
| Analysis |  |  |  |  | 32
|  | Update previous documentation | Team | Kory, Connor, Matt, Jimin | 8
|  | New Documentation | Team | Kory, Connor, Matt, Jimin | 8
|  | Presentation Video | Team | Kory, Connor, Matt, Jimin | 8
|  | Manual testing | Team | Kory, Connor, Matt, Jimin | 4
|  | Bug fix as required | Team | Kory, Connor, Matt, Jimin | 4
Total | [5 empty] | 474 |  | 267